## Gantt Chart
Gantt Chart — AR Wardrobe Trial
2D Camera-Based Virtual Dressing Room ¦ 8-Week Software Engineering Project
Task | Start Week | End Week | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Project planning & requirements | 1 | 1 | ■
Environment & technology setup | 1 | 2 | ■ | ■
Webcam / OpenCV frame capture | 2 | 3 |  | ■ | ■
MediaPipe Pose integration | 2 | 3 |  | ■ | ■
Body landmark extraction & tracking | 3 | 4 |  |  | ■ | ■
Person segmentation integration | 3 | 4 |  |  | ■ | ■
Clothing dataset & transparent PNG assets | 1 | 3 | ■ | ■ | ■
Body measurement / position / scale estimation | 3 | 4 |  |  | ■ | ■
2D clothing resize & positioning | 4 | 5 |  |  |  | ■ | ■
Virtual try-on compositing & layering | 4 | 6 |  |  |  | ■ | ■ | ■
Outfit selection / switching UI | 6 | 7 | [5 empty] | ■ | ■
Size recommendation module | 5 | 6 |  |  |  |  | ■ | ■
Fit evaluation module | 5 | 6 |  |  |  |  | ■ | ■
Gesture-based interaction | 6 | 7 | [5 empty] | ■ | ■
System integration & real-time optimization | 7 | 8 | [6 empty] | ■ | ■
Testing, debugging & accuracy evaluation | 7 | 8 | [6 empty] | ■ | ■
Documentation, final demo & presentation | 6 | 8 | [5 empty] | ■ | ■ | ■

## Canva Data
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Project planning & requirements | ●
Environment & technology setup | ● | ●
Webcam / OpenCV frame capture |  | ● | ●
MediaPipe Pose integration |  | ● | ●
Body landmark extraction & tracking |  |  | ● | ●
Person segmentation integration |  |  | ● | ●
Clothing dataset & transparent PNG assets | ● | ● | ●
Body measurement / position / scale estimation |  |  | ● | ●
2D clothing resize & positioning |  |  |  | ● | ●
Virtual try-on compositing & layering |  |  |  | ● | ● | ●
Outfit selection / switching UI | [5 empty] | ● | ●
Size recommendation module |  |  |  |  | ● | ●
Fit evaluation module |  |  |  |  | ● | ●
Gesture-based interaction | [5 empty] | ● | ●
System integration & real-time optimization | [6 empty] | ● | ●
Testing, debugging & accuracy evaluation | [6 empty] | ● | ●
Documentation, final demo & presentation | [5 empty] | ● | ● | ●